## Cover Page
Airport Management System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy Project Solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Airport Management System Project ID:A007 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Initial Selection | All Users | As User I want the system to allow the user to choose Admin / Manager / pilot Login/Registration | 1-Screen should display the option for Admin login / Registration and Manager login / Registration and Pilot login / Registration | Critical
US_2 | Employee Registration | Employee | As Employee I want the system to procure the fundamental details of the Manager | 1-When the Employee clicks on the registration link, it should re-direct to registration form. 2-Employee needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, DOB, Gender, Contact Number, Employee Id, Password etc. Employee id - should be auto generated DOB should selected from a drop down calendar Validation - Age should not be less than 18 should be checked. Contact number - 10 digits password- min length of 6 with special characters should be incorporated. Employee designation should be field with 2 role - Manage, Pilot. Use Radio button/Checkbox/drop down to select the option. 3-Before entering the next field, each field should be validated and appropriate error message should be displayed near the corresponding text box. 4-Employee failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7-Admin should be able to view the New Managers registration 8-Admin should approve / reject the Manager Request. 9-If rejected, the Manager should not be allowed to login with the registered credentials 10-Manager should be notified upon approval/rejection while trying to enter the application. | Critical
US_3 | Employee Authentication | Employee | As Employee I want the system to authenticate the Manager credentials of the registered Manager. | A registered Employee – is able click ‘Login’ link, after keying in ‘Employee ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_4 | Admin Authentication | Admin | As Admin I want the system to authenticate the credentials of the registered Admin. | 1- Admin User id and password can be preloaded in the database and use it to login into the system. 2- On keying in ‘Admin ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_5 | View registration request | Admin | As Admin I want the system to allow Admin to view the registration request | 1-Admin should be able to view the registration request awaiting approval | Critical
US_6 | Approve / Deny manager registration | Admin | As Admin I want the system to allow admin to approve or deny the registration request. | 1-Admin should be able to approve or deny the registration request. 2-Upon approval, Manager should be able to log in successfully. 3-Upon denial, message - "Your Registration is denied by Admin" should be display when they tried to log in. | Medium
US_7 | Add planes / update planes | Admin | As Admin I want to add/ update plane details. | 1-On clicking “Add Planes”, it should redirect to the page to add Plane. 2-Admin should be able to update the mandatory fields of the Planes. Plane id, Model number, Purchase date, Last serviced date etc can be fields. Note - Trainees can add more fields as appropriate. Use drop downs, radio buttons, check box options wherever applicable. 3-Clicking ‘Submit’ should validate the datatype constraints for each field 4-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7-Admin should be able to view the list of planes by clicking “View Planes” link. 8-On clicking the Plane ID, the system should display the details of the planes. Plane Id should be used as primary key the DB and should not be editable. 9-Admin should be able to update the details of the plane on clicking “Update details” button 10-On clicking “Save” button, the updated details should be saved to the database. Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Critical
US_8 | Update Flight Plan | Pilot | As Pilot I want the system to allow Pilot to update the flight plan. | 1-Pilot on clicking Update Flight Plan should be redirected to the Flight Plan update page. 2-Pilot should update mandatory fields - departure location, waypoints, estimated time of arrival, destination location, alternate airports, aircraft information, and the pilot’s information. 3-Clicking ‘Submit’ should validate the datatype constraints for each field 4-Pilot failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. Note - Learn about airport management to get to know on the different terminologies used in the Airport management system. | Critical
US_9 | Update Pre-flight mode | Pilot | As Pilot I want the system to gather information necessary to enter flight mode. | 1-Pilot should be able to update the pre flight mode checklist. 2- On clicking the Pre flight mode tab, all the flight that requires pre flight check should be displayed. 3-On clicking the flight the pilot want to update, it should open the checklist form. 4- Pilot should update the checklist 5-Manager/Pilot should be able to view it https://ardupilot.org/copter/docs/checklist.html Few checklist questions can be taken from this website. | Medium
US_10 | Update Post-flight mode | Pilot | As Pilot I want system to gather information during flight mode. It should display the information regarding future flights. | 1-Pilot should be able to update the post flight mode checklist. 2- On clicking the post flight mode tab, all the flight that requires post flight check should be displayed. 3-On clicking the flight the pilot want to update, it should open the checklist form. 4- Pilot should update the checklist 5-Manager/Pilot should be able to view it https://www.flyingmag.com/technique/tip-week/post-flight-procedures/ Check this to know more about Post flight procedure | Medium
US_11 | Update Resources | Admin | As Admin I want the system to update the Waypoints, maps, and routes. | 1-Admin should be able to update the Resource details which is required for the pilot. 2-Admin should be able to update the Waypoints, maps, and routes. Waypoint - A stopping point that is along a route in which a set of coordinates identify a point. Route - Collection of waypoints with a departure and a destination airport. | Medium
US_12 | Target Generation Facility | Pilot | As Pilot I want to know information about current flights or registered flight plans. | 1-Pilot should be able to get information about current flights or registered flight plans. | Medium
US_13 | Add pilots work schedule | Admin | As Admin I want the system to add pilot’s work schedule details. | 1-Admin should be able to add pilot’s work schedule details. | Critical
US_14 | View schedule | Pilot | As Pilot I want to view the schedule | 1-Pilot on clicking view the schedule should redirect to the Pilot schedule page 2-The page should display the Pilots schedule. Pilot should have the option to view that days schedule, Weekly schedule and the schedule for the month. | Critical
US_15 | Request rescheduling | Pilot | As pilot I want to reschedule my work time. | 1-Pilot should be able to raise a request for rescheduling the work schedule if required. | low
US_16 | View / approve rescheduling request | Admin | As Admin I want to view and approve the rescheduling request. | 1-Admin should be able to view the reschedule request from the pilot. 2-On clicking each request ID, it should display the details. 3-Admin should be able to approve / deny the request. | low
US_17 | Update schedule | Admin | As Admin I want to update pilot’s work schedule details. | 1-Upon approval, Admin should be able to update pilot’s work schedule details. | low
US_18 | Add Hangars | Admin | As Admin I want to add Hangar details. A hangar is a closed building structure to hold aircraft or spacecraft. ... Hangars are used for protection from the weather, direct sunlight and for maintenance, repair, manufacture, assembly and storage of aircraft. | 1-On clicking “Add Hangars”, it should redirect to the page to add Plane. 2-Admin should be able to update the mandatory fields of the Hangars 3-Clicking ‘Submit’ should validate the datatype constraints for each field 4-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 7-Admin should be able to view the list of Hangars by clicking “View Hangars” link. 8-On clicking the Plane ID, the system should display the details of the Hangars. 9-Admin should be able to update the details of the plan on clicking “Update details” button 10-On clicking “Save” button, the updated details should be saved to the database. Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | Critical
US_19 | Allotting planes to the Hangar | Manager | As Manager I want to allot planes to Hangar. | 1-When Manager clicks Allot Hangar, the system should display the list of Hangars available and the list of planes waiting for hanger 2-Manager should have the option to select the available hangar and allot it for a plane | Medium
US_20 | Update Hangar status | Manager | As Manager I want to update the Hangar details. | 1-After allotting Manager should update the status as Available / Allotted 2-Manager on clicking “View Hangar Status”, the page should display the list of all Hangars with status | Medium
US_21 | View Hangar Status | Admin/Pilot | As Admin/Pilot I want to view the Hangar details. | 1-Admin on clicking Reports should redirect to the reporting page. 2-It should display drop down Pilot schedule, Hanger allotment, Plane details. 3-On selecting Pilot schedule, it should display the Pilots work schedule. 4-On clicking Hanger allotment, should display all the available Hangers and the allotment details 5-On clicking Plane details., should display all the available Planes and the details | Medium
US_22 | Generate Report | Admin | As Admin I want to generate report on Pilot schedule, Hanger allotment, Plane details. | 1-During registration, System should pop up three secret questions for Password recovery. 2-When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. | low
US_23 | Other validations | Admin | As Admin I want the system to have validations like Forget User ID, Forget Password | 1-When the user clicks Forgot Password, system should ask for the User ID and secret questions. Email id and contact number can also be used along with the secret questions to uniquely identify the User as Same answers can be given by many users 2-On answering the questions correctly, the password reset page should be displayed. 3-On entering the details in the password reset page, password should be validated 4-On clicking Submit, the details should be saved to the Database | low
US_24 | Help | Admin | As Admin I want Page to assist the users to report technical issues | 1-Page to display a form that allows user to report the technical issues. Issue Description Send Button Portal to display the Contact number to report issues User should be able to raise the help and managers should be able to answer the query | low
US_25 | Manager / Admin logoff | All Users | Ability of the system to enable Manager / Admin to logoff | 1-Option to log off from the system. | Critical

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000